{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Daten zum Marketingplan","Listendaten"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Daten zum Marketingplan","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Daten zum Marketingplan",null,"STATUSFARBENLEGENDE EIN-/AUSSCHALTEN"]
[null,"Listen zum Marketingplan"]
[{"$nulls":3},"Nicht begonnen","In Bearbeitung","Verzögert","Abgeschlossen","Benutzerdef. 1","Benutzerdef. 2","Benutzerdef. 3","Benutzerdef. 4"]
[{"$nulls":3},"EIN","EIN","AUS","EIN","AUS","AUS","AUS","AUS"]
[null,"AUFGABE","STATUS","BESITZER","ZUGEWIESEN AN","ERWARTET\nANFANGSDATUM","ERWARTET\nENDDATUM","TATSÄCHLICH \nANFANGSDATUM ","TATSÄCHLICH \nENDDATUM ","GESCHÄTZTE KOSTEN","TATSÄCHLICH \nKOSTEN"]
[null,"Produktanalyse","In Bearbeitung","Detlev H.","Detlev H.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":1500,"d":"1,500 €"},{"v":1250,"d":"1,250 €"}]
[null,"Storyboards entwerfen","In Bearbeitung","Hanno S.","Detlev H.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":2000,"d":"2,000 €"},{"v":1840,"d":"1,840 €"}]
[null,"Storyboardentwurf überprüfen","Abgeschlossen","Hanno S.","Detlev H.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":1450,"d":"1,450 €"}]
[null,"Forschungsanalyse Phase I","Verzögert","Lothar M.","Adrian W.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":3000,"d":"3,000 €"},{"v":3200,"d":"3,200 €"}]
[null,"Erstellung von Anzeigeninhalten Phase I","Verzögert","Lothar M.","Gabriel M.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":500,"d":"500 €"}]
[null,"Produktanforderungsdefinitionen","Verzögert","Lothar M.","Leonie B.",{"$nulls":4},{"v":575,"d":"575 €"},{"v":125,"d":"125 €"}]
[null,"Prototypen-Entwicklungsspezifikationen","In Bearbeitung","Lothar M.","Adele M.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":1750,"d":"1,750 €"}]
[null,"Qualitätskontrolle, Statusberichte","In Bearbeitung","Hanno S.","Lothar M.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":925,"d":"925 €"},{"v":250,"d":"250 €"}]
[null,"Storyboards erstellen","Nicht begonnen","Hanno S.","Detlev H.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":2000,"d":"2,000 €"},{"v":1840,"d":"1,840 €"}]
[null,"Storyboards mit Grafikern überprüfen","Verzögert","Hanno S.","Detlev H.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":1450,"d":"1,450 €"}]
[null,"Forschungsanalyse Phase II","Abgeschlossen","Lothar M.","Adrian W.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":3000,"d":"3,000 €"},{"v":3200,"d":"3,200 €"}]
[null,"Erstellung von Anzeigeninhalten Phase II","Nicht begonnen","Lothar M.","Gabriel M.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":500,"d":"500 €"}]

{"sheet":"Listendaten","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Listen zum Marketingplan"]
[null,"Daten zum Marketingplan"]
[null,"NAME","POSITION"]
[null,"Detlev H.","Marketingspezialist"]
[null,"Hanno S.","Marketingmanager"]
[null,"Lothar M.","Projektmanager"]
[null,"Kai S.","Marketinganalyst"]
[null,"Adrian W.","Forschungsleiter"]
[null,"Gabriel M.","Marketingspezialist"]
[null,"Leonie B.","Marketinganalyst"]
[null,"Adele M.","Partner-Marketingmanager"]