## Marketing plan data
Marketing plan data |  | STATUS COLOUR LEGEND & TOGGLE
Marketing plan lists
|  | Not started | In progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | OFF | ON | OFF | OFF | OFF | OFF
TASK | STATUS | OWNER | ASSIGNED TO | ANTICIPATED START DATE | ANTICIPATED END DATE | ACTUAL START DATE | ACTUAL END DATE | ESTIMATED COST | ACTUAL COST
Product analysis | In progress | John C. | John C. | 2018-07-01 | 2018-08-01 | 2018-06-28 |  | 1500 | 1250
Design storyboards | In progress | Mark M. | John C. | 2018-07-15 | 2018-08-15 | 2018-07-13 |  | 2000 | 1840
Review storyboard design | Complete | Mark M. | John C. | 2018-08-01 | 2018-08-20 |  |  | 1450
Research analysis phase I | Delayed | Kamil A. | Andrew L. | 2018-06-01 | 2018-07-01 | 2018-06-01 | 2018-06-28 | 3000 | 3200
Advertising content creation phase I | Delayed | Kamil A. | Timothy S. | 2018-09-01 | 2018-09-15 |  |  | 500
Product requirement definitions | Delayed | Kamil A. | Vivian A. |  |  |  |  | 575 | 125
Prototype development specifications | In progress | Kamil A. | Gabe F. | 2018-09-12 | 2018-09-25 |  |  | 1750
Quality control, progress reports | In progress | Mark M. | Kamil A. | 2018-07-01 | 2018-10-01 | 2018-07-01 |  | 925 | 250
Create storyboards | Not started | Mark M. | John C. | 2018-07-15 | 2018-08-15 | 2018-07-13 |  | 2000 | 1840
Review storyboards with graphic artists | Delayed | Mark M. | John C. | 2018-08-01 | 2018-08-20 |  |  | 1450
Research analysis phase II | Complete | Kamil A. | Andrew L. | 2018-06-01 | 2018-07-01 | 2018-06-01 | 2018-06-28 | 3000 | 3200
Advertising content creation phase II | Not started | Kamil A. | Timothy S. | 2018-09-01 | 2018-09-15 |  |  | 500
MARKETING PLAN LISTS

## List data
Marketing plan lists
Marketing plan data
NAME | TITLE
John C. | Marketing Specialist
Mark M. | Marketing Manager
Kamil A. | Project Manager
Phil G. | Marketing Analyst
Andrew L. | Research Coordinator
Timothy S. | Marketing Specialist
Vivian A. | Marketing Analyst
Gabe F. | Associate Marketing Manager
MARKETING PLAN DATA