{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketing plan data","List data"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Marketing plan data","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"merged":[[0,3,0,10],[1,1,3,1],[1,3,1,10]]}
[null,"Marketing plan data"]
[null,"Marketing plan lists",null,"Status colour legend and toggle"]
[{"$nulls":3},"Not started","In progress","Delayed","Complete","Custom 1","Custom 2","Custom 3","Custom 4"]
[{"$nulls":3},"ON","ON","ON","ON","ON","ON","ON","ON"]
[]
[null,"Task","Status","Owner","Assigned to","Anticipated\nStart date","Anticipated\nEnd date","Actual\nStart date","Actual\nEnd date","Estimated cost","Actual\nCost"]
[null,"Product analysis","Not started","John C.","John C.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},null,{"v":1500,"d":"£1,500"},{"v":1250,"d":"£1,250"}]
[null,"Design storyboards","In progress","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"£2,000"},{"v":1840,"d":"£1,840"}]
[null,"Review storyboard design","Delayed","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"£1,450"}]
[null,"Research analysis phase I","Complete","Kamil A.","Andrew L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"£3,000"},{"v":3200,"d":"£3,200"}]
[null,"Advertising content creation phase I","Custom 1","Kamil A.","Timothy S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"£500"}]
[null,"Product requirement definitions","Custom 2","Timothy S.","Vivian A.",{"$nulls":4},{"v":575,"d":"£575"},{"v":125,"d":"£125"}]
[null,"Prototype development specifications","Custom 3","Kamil A.","Gabe F.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2019-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2019-09-25"},null,null,{"v":1750,"d":"£1,750"}]
[null,"Quality control, progress reports","Custom 4","Mark M.","Kamil A.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2019-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},null,{"v":925,"d":"£925"},{"v":250,"d":"£250"}]
[null,"Create storyboards","Not started","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"£2,000"},{"v":1840,"d":"£1,840"}]
[null,"Review storyboards with graphic artists","Delayed","Mark M.","John C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"£1,450"}]
[null,"Research analysis phase II","Complete","Kamil A.","Andrew L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"£3,000"},{"v":3200,"d":"£3,200"}]
[null,"Advertising content creation phase II","Not started","Kamil A.","Timothy S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"£500"}]

{"sheet":"List data","index":1,"n_rows":12,"n_cols":3,"rows_kept":12,"merged":[[0,1,0,2],[1,1,1,2]]}
[null,"Marketing plan lists"]
[null,"Marketing plan data"]
[]
[null,"Name","Title"]
[null,"John C.","Marketing Specialist"]
[null,"Mark M.","Marketing Manager"]
[null,"Kamil A.","Project Manager"]
[null,"Phil G.","Marketing Analyst"]
[null,"Andrew L.","Research Coordinator"]
[null,"Timothy S.","Marketing Specialist"]
[null,"Vivian A.","Marketing Analyst"]
[null,"Gabe F.","Associate Marketing Manager"]