{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Data Rencana Pemasaran","Data Daftar"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Data Rencana Pemasaran","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Data Rencana Pemasaran",null,"TOMBOL ALIH & LEGENDA WARNA STATUS"]
[null,"Daftar Rencana Pemasaran"]
[{"$nulls":3},"Belum Dimulai","Dalam Proses","Ditunda","Selesai","Kustom 1","Kustom 2","Kustom 3","Kustom 4"]
[{"$nulls":3},"AKTIF","AKTIF","NONAKTIF","AKTIF","NONAKTIF","NONAKTIF","NONAKTIF","NONAKTIF"]
[null,"TUGAS","STATUS","PENANGGUNG JAWAB","DITUGASKAN KEPADA","PERKIRAAN\nTANGGAL MULAI","PERKIRAAN\nTANGGAL BERAKHIR","TANGGAL MULAI \nSEBENARNYA ","TANGGAL BERAKHIR \nSEBENARNYA ","BIAYA PERKIRAAN","BIAYA \nSEBENARNYA"]
[null,"Menganalisis Produk","Dalam Proses","Johan C.","Johan C.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":15000000,"d":"Rp15,000,000"},{"v":12500000,"d":"Rp12,500,000"}]
[null,"Mendesain Sketsa Naskah","Dalam Proses","Markus M.","Johan C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":20000000,"d":"Rp20,000,000"},{"v":18400000,"d":"Rp18,400,000"}]
[null,"Meninjau Desain Sketsa Naskah","Selesai","Markus M.","Johan C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":14500000,"d":"Rp14,500,000"}]
[null,"Analisis Penelitian Tahap I","Ditunda","Kemal A.","Andri L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":30000000,"d":"Rp30,000,000"},{"v":32000000,"d":"Rp32,000,000"}]
[null,"Membuat Konten Periklanan Tahap I","Ditunda","Kemal A.","Tomo S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":5000000,"d":"Rp5,000,000"}]
[null,"Definisi Persyaratan Produk","Ditunda","Kemal A.","Vina A.",{"$nulls":4},{"v":5750000,"d":"Rp5,750,000"},{"v":1250000,"d":"Rp1,250,000"}]
[null,"Spesifikasi Pengembangan Prototipe","Dalam Proses","Kemal A.","Gani F.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":17500000,"d":"Rp17,500,000"}]
[null,"Kontrol Kualitas, Laporan Kemajuan","Dalam Proses","Markus M.","Kemal A.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":9250000,"d":"Rp9,250,000"},{"v":2500000,"d":"Rp2,500,000"}]
[null,"Membuat Sketsa Naskah","Belum Dimulai","Markus M.","Johan C.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":20000000,"d":"Rp20,000,000"},{"v":18400000,"d":"Rp18,400,000"}]
[null,"Meninjau Sketsa Naskah dengan Seniman Grafis","Ditunda","Markus M.","Johan C.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":14500000,"d":"Rp14,500,000"}]
[null,"Analisis Penelitian Tahap II","Selesai","Kemal A.","Andri L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":30000000,"d":"Rp30,000,000"},{"v":32000000,"d":"Rp32,000,000"}]
[null,"Membuat Konten Periklanan Tahap II","Belum Dimulai","Kemal A.","Tomo S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":5000000,"d":"Rp5,000,000"}]

{"sheet":"Data Daftar","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Daftar Rencana Pemasaran"]
[null,"Data Rencana Pemasaran"]
[null,"NAMA","JABATAN"]
[null,"Johan C.","Spesialis Pemasaran"]
[null,"Markus M.","Manajer Pemasaran"]
[null,"Kemal A.","Manajer Proyek"]
[null,"Pijar G.","Analis Pemasaran"]
[null,"Andri L.","Koordinator Riset"]
[null,"Tomo S.","Spesialis Pemasaran"]
[null,"Vina A.","Analis Pemasaran"]
[null,"Gani F.","Asisten Manajer Pemasaran"]