{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Data Rancangan Pemasaran","Data Senarai"],"not_rendered":{"defined_names":13},"read":"whole","date_system":"1900"}

{"sheet":"Data Rancangan Pemasaran","index":0,"n_rows":24,"n_cols":11,"rows_kept":24}
[]
[null,"Data Rancangan Pemasaran"]
[{"$nulls":3},"PENUNJUK & TOGOL WARNA STATUS"]
[]
[]
[{"$nulls":3},"Belum Mula","Sedang Berjalan","Ditangguhkan","Selesai","Tersuai 1","Tersuai 2","Tersuai 3","Tersuai 4"]
[{"$nulls":3},"HIDUPKAN","HIDUPKAN","MATIKAN","HIDUPKAN","MATIKAN","MATIKAN","MATIKAN","MATIKAN"]
[]
[{"$nulls":5},"DIJANGKA",null,"SEBENAR",null,"KOS"]
[]
[]
[null,"TUGAS","STATUS","PEMILIK","DITUGASKAN KEPADA","TARIKH MULA","TARIKH TAMAT","TARIKH MULA ","TARIKH TAMAT ","ANGGARAN","SEBENAR"]
[null,"Analisis Produk","Sedang Berjalan","John C.","John C.","2012-07-01","2012-08-01","2012-06-28",null,{"v":1500,"d":"RM1,500"},{"v":1250,"d":"RM1,250"}]
[null,"Reka Bentuk Papan Cerita","Sedang Berjalan","Mark M.","John C.","2012-07-15","2012-08-15","2012-07-13",null,{"v":2000,"d":"RM2,000"},{"v":1840,"d":"RM1,840"}]
[null,"Semak Semula Reka Bentuk Papan Cerita","Selesai","Mark M.","John C.","2012-08-01","2012-08-20",null,null,{"v":1450,"d":"RM1,450"}]
[null,"Analisis Penyelidikan Fasa I","Ditangguhkan","Kamil A.","Andrew L.","2012-06-01","2012-07-01","2012-06-01","2012-06-28",{"v":3000,"d":"RM3,000"},{"v":3200,"d":"RM3,200"}]
[null,"Penciptaan Kandungan Pengiklanan Fasa I","Ditangguhkan","Kamil A.","Timothy S.","2012-09-01","2012-09-15",null,null,{"v":500,"d":"RM500"}]
[null,"Definisi Keperluan Produk","Ditangguhkan","Kamil A.","Vivian A.",{"$nulls":4},{"v":575,"d":"RM575"},{"v":125,"d":"RM125"}]
[null,"Spesifikasi Pembangunan Prototaip","Sedang Berjalan","Kamil A.","Gabe F.","2012-09-12","2012-09-25",null,null,{"v":1750,"d":"RM1,750"}]
[null,"Kawalan Kualiti, Laporan Kemajuan","Sedang Berjalan","Mark M.","Kamil A.","2012-07-01","2012-10-01","2012-07-01",null,{"v":925,"d":"RM925"},{"v":250,"d":"RM250"}]
[null,"Cipta Papan Cerita","Belum Mula","Mark M.","John C.","2012-07-15","2012-08-15","2012-07-13",null,{"v":2000,"d":"RM2,000"},{"v":1840,"d":"RM1,840"}]
[null,"Semak Semula Papan Cerita dengan Artis Grafik","Selesai","Mark M.","John C.","2012-08-01","2012-08-20",null,null,{"v":1450,"d":"RM1,450"}]
[null,"Analisis Penyelidikan Fasa II","Selesai","Kamil A.","Andrew L.","2012-06-01","2012-07-01","2012-06-01","2012-06-28",{"v":3000,"d":"RM3,000"},{"v":3200,"d":"RM3,200"}]
[null,"Penciptaan Kandungan Pengiklanan Fasa II","Belum Mula","Kamil A.","Timothy S.","2012-09-01","2012-09-15",null,null,{"v":500,"d":"RM500"}]

{"sheet":"Data Senarai","index":1,"n_rows":14,"n_cols":3,"rows_kept":14}
[]
[null,"Senarai Rancangan Pemasaran"]
[]
[]
[]
[null,"NAMA","TAJUK"]
[null,"John C.","Pakar Pemasaran"]
[null,"Mark M.","Pengurus Pemasaran"]
[null,"Kamil A.","Pengurus Projek"]
[null,"Phil G.","Juruanalisis Pemasaran"]
[null,"Andrew L.","Penyelaras Penyelidikan"]
[null,"Timothy S.","Pakar Pemasaran"]
[null,"Vivian A.","Juruanalisis Pemasaran"]
[null,"Gabe F.","Pengurus Pemasaran Bersekutu"]