{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketingplangegevens","Overzicht gegevens"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Marketingplangegevens","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Marketingplangegevens",null,"LEGENDA EN WISSELKNOP STATUSKLEUR"]
[null,"Marketingplanlijsten"]
[{"$nulls":3},"Niet gestart","Wordt uitgevoerd","Vertraagd","Voltooid","Aangepast 1","Aangepast 2","Aangepast 3","Aangepast 4"]
[{"$nulls":3},"AAN","AAN","UIT","AAN","UIT","UIT","UIT","UIT"]
[null,"TAAK","STATUS","EIGENAAR","TOEGEWEZEN AAN","VERWACHTE\nBEGINDATUM","VERWACHTE\nEINDDATUM","WERKELIJKE \nBEGINDATUM ","WERKELIJKE \nEINDDATUM ","GESCHATTE KOSTEN","WERKELIJKE \nKOSTEN"]
[null,"Productanalyse","Wordt uitgevoerd","Joep S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":9000,"d":"€ 9,000"},{"v":7500,"d":"€ 7,500"}]
[null,"Storyboards ontwerpen","Wordt uitgevoerd","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":12000,"d":"€ 12,000"},{"v":11040,"d":"€ 11,040"}]
[null,"Storyboardontwerp controleren","Voltooid","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":8700,"d":"€ 8,700"}]
[null,"Onderzoeksanalyse fase I","Vertraagd","Hakan K.","Arnaud L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":18000,"d":"€ 18,000"},{"v":19200,"d":"€ 19,200"}]
[null,"Reclame-inhoudscreatie fase I","Vertraagd","Hakan K.","Jan S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":3000,"d":"€ 3,000"}]
[null,"Definities productvereisten","Vertraagd","Hakan K.","Sabien A.",{"$nulls":4},{"v":3450,"d":"€ 3,450"},{"v":750,"d":"€ 750"}]
[null,"Specificaties prototypeontwikkeling","Wordt uitgevoerd","Hakan K.","Gwenda R.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":10500,"d":"€ 10,500"}]
[null,"Kwaliteitscontrole, voortgangsrapporten","Wordt uitgevoerd","Maarten S.","Hakan K.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":5550,"d":"€ 5,550"},{"v":1500,"d":"€ 1,500"}]
[null,"Storyboards maken","Niet gestart","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":12000,"d":"€ 12,000"},{"v":11040,"d":"€ 11,040"}]
[null,"Storyboards controleren met grafisch ontwerpers","Vertraagd","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":8700,"d":"€ 8,700"}]
[null,"Onderzoeksanalyse fase II","Voltooid","Hakan K.","Arnaud L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":18000,"d":"€ 18,000"},{"v":19200,"d":"€ 19,200"}]
[null,"Reclame-inhoudscreatie fase II","Niet gestart","Hakan K.","Jan S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":3000,"d":"€ 3,000"}]

{"sheet":"Overzicht gegevens","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Marketingplanlijsten"]
[null,"Marketingplangegevens"]
[null,"NAAM","TITEL"]
[null,"Joep S.","Marketingspecialist"]
[null,"Maarten S.","Marketingmanager"]
[null,"Hakan K.","Projectmanager"]
[null,"Floris K.","Marketinganalist"]
[null,"Arnaud L.","Onderzoekscoördinator"]
[null,"Jan S.","Marketingspecialist"]
[null,"Sabien A.","Marketinganalist"]
[null,"Gwenda R.","Collega-marketingmanager"]