{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Marketingplangegevens","Overzicht gegevens"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Marketingplangegevens","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"merged":[[0,3,0,10],[1,1,3,1],[1,3,1,10]]}
[null,"Marketingplangegevens"]
[null,"Marketingplanlijsten",null,"Legenda en wisselknop statuskleur"]
[{"$nulls":3},"Niet gestart","Wordt uitgevoerd","Vertraagd","Voltooid","Aangepast 1","Aangepast 2","Aangepast 3","Aangepast 4"]
[{"$nulls":3},"AAN","AAN","AAN","AAN","AAN","AAN","AAN","AAN"]
[]
[null,"Taak","Status","Eigenaar","Toegewezen aan","Verwacht\nBegindatum","Verwacht\nEinddatum","Werkelijk\nBegindatum","Werkelijk\nEinddatum","Geschatte kosten","Werkelijk\nKosten"]
[null,"Productanalyse","Niet gestart","Joep S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},null,{"v":1500,"d":"€ 1,500"},{"v":1250,"d":"€ 1,250"}]
[null,"Storyboards ontwerpen","Wordt uitgevoerd","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"€ 2,000"},{"v":1840,"d":"€ 1,840"}]
[null,"Storyboardontwerp controleren","Vertraagd","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"€ 1,450"}]
[null,"Onderzoeksanalyse fase I","Voltooid","Hakan K.","Arnaud L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"€ 3,000"},{"v":3200,"d":"€ 3,200"}]
[null,"Reclame-inhoudscreatie fase I","Aangepast 1","Hakan K.","Jan S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"€ 500"}]
[null,"Definities productvereisten","Aangepast 2","Jan S.","Sabien A.",{"$nulls":4},{"v":575,"d":"€ 575"},{"v":125,"d":"€ 125"}]
[null,"Specificaties prototypeontwikkeling","Aangepast 3","Hakan K.","Gwenda R.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2019-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2019-09-25"},null,null,{"v":1750,"d":"€ 1,750"}]
[null,"Kwaliteitscontrole, voortgangsrapporten","Aangepast 4","Maarten S.","Hakan K.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2019-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},null,{"v":925,"d":"€ 925"},{"v":250,"d":"€ 250"}]
[null,"Storyboards maken","Niet gestart","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2019-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2019-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2019-07-13"},null,{"v":2000,"d":"€ 2,000"},{"v":1840,"d":"€ 1,840"}]
[null,"Storyboards controleren met grafisch ontwerpers","Vertraagd","Maarten S.","Joep S.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2019-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2019-08-20"},null,null,{"v":1450,"d":"€ 1,450"}]
[null,"Onderzoeksanalyse fase II","Voltooid","Hakan K.","Arnaud L.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2019-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2019-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2019-06-28"},{"v":3000,"d":"€ 3,000"},{"v":3200,"d":"€ 3,200"}]
[null,"Reclame-inhoudscreatie fase II","Niet gestart","Hakan K.","Jan S.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2019-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2019-09-15"},null,null,{"v":500,"d":"€ 500"}]

{"sheet":"Overzicht gegevens","index":1,"n_rows":12,"n_cols":3,"rows_kept":12,"merged":[[0,1,0,2],[1,1,1,2]]}
[null,"Marketingplanlijsten"]
[null,"Marketingplangegevens"]
[]
[null,"Naam","Titel"]
[null,"Joep S.","Marketingspecialist"]
[null,"Maarten S.","Marketingmanager"]
[null,"Hakan K.","Projectmanager"]
[null,"Floris K.","Marketinganalist"]
[null,"Arnaud L.","Onderzoekscoördinator"]
[null,"Jan S.","Marketingspecialist"]
[null,"Sabien A.","Marketinganalist"]
[null,"Gwenda R.","Collega-marketingmanager"]