{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["Dane planu marketingowego","Dane listy"],"not_rendered":{"defined_names":18},"read":"whole","date_system":"1900"}

{"sheet":"Dane planu marketingowego","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[0,1,0,2],[0,3,0,10],[1,1,3,1]]}
[null,"Dane planu marketingowego",null,"LEGENDA I PRZEŁĄCZNIK KOLORÓW STANU"]
[null,"Listy planów marketingowych"]
[{"$nulls":3},"Nierozpoczęte","W toku","Opóźnione","Wykonane","Niestandardowe 1","Niestandardowe 2","Niestandardowe 3","Niestandardowe 4"]
[{"$nulls":3},"WŁ.","WŁ.","WYŁ.","WŁ.","WYŁ.","WYŁ.","WYŁ.","WYŁ."]
[null,"ZADANIE","STAN","WŁAŚCICIEL","PRZYPISANE DO","PRZEWIDYWANA\nDATA ROZPOCZĘCIA","PRZEWIDYWANA\nDATA ZAKOŃCZENIA","RZECZYWISTA \nDATA ROZPOCZĘCIA ","RZECZYWISTA \nDATA ZAKOŃCZENIA ","SZACOWANY KOSZT","RZECZYWISTY \nKOSZT"]
[null,"Analiza produktu","W toku","Jan K.","Jan K.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},null,{"v":4500,"d":"4,500 zł"},{"v":3750,"d":"3,750 zł"}]
[null,"Opracowanie projektu scenorysów","W toku","Marek P.","Jan K.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":6000,"d":"6,000 zł"},{"v":5520,"d":"5,520 zł"}]
[null,"Przegląd projektu scenorysów","Wykonane","Marek P.","Jan K.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":4350,"d":"4,350 zł"}]
[null,"Analiza badań — faza I","Opóźnione","Piotr T.","Szymon W.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":9000,"d":"9,000 zł"},{"v":9600,"d":"9,600 zł"}]
[null,"Tworzenie treści reklamowych — faza I","Opóźnione","Piotr T.","Tomasz C.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":1500,"d":"1,500 zł"}]
[null,"Definicje wymagań dotyczących produktów","Opóźnione","Piotr T.","Luiza B.",{"$nulls":4},{"v":1725,"d":"1,725 zł"},{"v":375,"d":"375 zł"}]
[null,"Specyfikacje prototypów","W toku","Piotr T.","Jacek K.",{"$f":"DATE(YEAR(TODAY()),9,12)","v":"2018-09-12"},{"$f":"DATE(YEAR(TODAY()),9,25)","v":"2018-09-25"},null,null,{"v":5250,"d":"5,250 zł"}]
[null,"Kontrola jakości, raporty o postępach","W toku","Marek P.","Piotr T.",{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),10,1)","v":"2018-10-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},null,{"v":2775,"d":"2,775 zł"},{"v":750,"d":"750 zł"}]
[null,"Tworzenie scenorysów","Nierozpoczęte","Marek P.","Jan K.",{"$f":"DATE(YEAR(TODAY()),7,15)","v":"2018-07-15"},{"$f":"DATE(YEAR(TODAY()),8,15)","v":"2018-08-15"},{"$f":"DATE(YEAR(TODAY()),7,13)","v":"2018-07-13"},null,{"v":6000,"d":"6,000 zł"},{"v":5520,"d":"5,520 zł"}]
[null,"Przegląd scenorysów wspólnie z grafikami","Opóźnione","Marek P.","Jan K.",{"$f":"DATE(YEAR(TODAY()),8,1)","v":"2018-08-01"},{"$f":"DATE(YEAR(TODAY()),8,20)","v":"2018-08-20"},null,null,{"v":4350,"d":"4,350 zł"}]
[null,"Analiza badań — faza II","Wykonane","Piotr T.","Szymon W.",{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),7,1)","v":"2018-07-01"},{"$f":"DATE(YEAR(TODAY()),6,1)","v":"2018-06-01"},{"$f":"DATE(YEAR(TODAY()),6,28)","v":"2018-06-28"},{"v":9000,"d":"9,000 zł"},{"v":9600,"d":"9,600 zł"}]
[null,"Tworzenie treści reklamowych — faza II","Nierozpoczęte","Piotr T.","Tomasz C.",{"$f":"DATE(YEAR(TODAY()),9,1)","v":"2018-09-01"},{"$f":"DATE(YEAR(TODAY()),9,15)","v":"2018-09-15"},null,null,{"v":1500,"d":"1,500 zł"}]

{"sheet":"Dane listy","index":1,"n_rows":11,"n_cols":3,"rows_kept":11,"merged":[[1,1,1,2]]}
[null,"Listy planów marketingowych"]
[null,"Dane planu marketingowego"]
[null,"IMIĘ I NAZWISKO","STANOWISKO"]
[null,"Jan K.","Specjalista ds. marketingu"]
[null,"Marek P.","Kierownik ds. marketingu"]
[null,"Piotr T.","Kierownik projektu"]
[null,"Sebastian K.","Analityk ds. marketingu"]
[null,"Szymon W.","Koordynator badań"]
[null,"Tomasz C.","Specjalista ds. marketingu"]
[null,"Luiza B.","Analityk ds. marketingu"]
[null,"Jacek K.","Z-ca kierownika ds. marketingu"]